## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understand project objectives and stock/ETF signal requirements | MUST HAVE | No Dependency | Zakkireddy Srihitha Reddy | 3- Completed
S2 | S1 | US-002 | Design system workflow and architecture (ML + APIs + Dashboard) | MUST HAVE | Lucidchart / Draw.io | Zakkireddy Srihitha Reddy | 3- Completed
S3 | S2 | US-003 | Set up development environment and integrate financial APIs | MUST HAVE | Python, APIs | Zakkireddy Srihitha Reddy | 3- Completed
S4 | S2 | US-004 | Perform data preprocessing and feature engineering | MUST HAVE | Pandas, NumPy | Zakkireddy Srihitha Reddy | 3- Completed
S5 | S3 | US-005 | Develop ML models (Random Forest, LSTM, Gradient Boosting) | MUST HAVE | Scikit-learn, TensorFlow | Zakkireddy Srihitha Reddy | 3- Completed
S6 | S4 | US-006 | Implement trading signal generation (Buy/Sell/Hold) | MUST HAVE | ML Models | Zakkireddy Srihitha Reddy | 3- Completed
S7 | S5 | US-007 | Develop backtesting engine using historical data | MUST HAVE | Historical Data APIs | Zakkireddy Srihitha Reddy | 2- In Progress
S8 | S6 | US-008 | Calculate performance metrics (Sharpe Ratio, Drawdown | SHOULD HAVE | Backtesting Module | Zakkireddy Srihitha Reddy | 2- In Progress
S9 | S7 | US-009 | Implement real-time alert system (Email/Slack) | SHOULD HAVE | Notification APIs | Zakkireddy Srihitha Reddy | 2- In Progress
S10 | S8 | US-010 | Develop interactive dashboard (Streamlit/Plotly) | MUST HAVE | Visualization Libraries | Zakkireddy Srihitha Reddy | 2- In Progress
S11 | S9 | US-011 | Integrate all modules into complete system | MUST HAVE | All Modules | Zakkireddy Srihitha Reddy | 2- In Progress
S12 | S10 | US-012 | Perform testing, deployment, and final presentation | MUST HAVE | Deployment Platform | Zakkireddy Srihitha Reddy | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 39 | 2 | 2 | 3.5 | 5 | 7 | 5.5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Project understanding & planning | 2026-02-02 | 2026-02-16 | Mosra Sanjana Reddy | Build | 3-Completed | 6 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Research stock & ETF signals | 2026-02-02 | 2026-02-07 | Palepu Sri Mahalakshmi | Coding | 3-Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | System architecture design | 2026-02-10 | 2026-02-15 | Mosra Sanjana Reddy | Design | 3-Completed | 8 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-002 | T-004 | Workflow diagram creation | 2026-02-10 | 2026-02-16 | Susekha P | Design | 3-Completed | 5 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-005 | API exploration & setup | 2026-02-12 | 2026-02-18 | Lokesh Avulapati | Integration Test | 3-Completed | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-002 | T-006 | Documentation preparation | 2026-02-14 | 2026-02-20 | Zakkireddy Srihitha Reddy | System Test | 3-Completed | 5 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-002 | T-007 | UI setup | 2026-02-15 | 2026-02-22 | Yash Kumar | Unit Test | 3-Completed | 3 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Initial lack of clarity in project scope | Reviewed project requirements and defined objectives
S1 | Day 2 | Difficulty identifying reliable data sources | Explored APIs like Yahoo Finance and Alpha Vantage
S1 | Day 3 | Limited understanding of ETF concepts | Studied financial concepts using tutorials and research papers
S1 | Day 4 | Complexity in understanding trading signals | Analyzed sample strategies and case studies
S1 | Day 5 | Challenges in requirement mapping | Broke requirements into smaller functional modules
S1 | Day 6 | Confusion in selecting design tools | Selected Draw.io for system workflow design
S1 | Day 7 | Minor issues in system architecture | Refined architecture and validated components
S1 | Day 8 | Difficulty in structuring workflow | Created step-by-step workflow diagrams
S1 | Day 9 | Time management challenges | Allocated fixed working hours and milestones
S1 | Day 10 | Minor inconsistencies in design | Standardized design and updated diagrams
S1 | Day 11 | No major issues | Continued development smoothly
S1 | Day 12 | No major issues | Maintained steady progress
S1 | Day 13 | Minor doubts in final design | Performed cross-verification and validation
S1 | Day 14 | No issues | Successfully completed sprint

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-01 | 2026-02-05 | Mosra Sanjana Reddy | Start better system design planning | Stop delaying critical decisions | Continue leading core development | Improved architecture and coordination
2 | S1 | 2026-02-01 | 2026-02-05 | Palepu Sri Mahalakshmi | Start deeper API understanding | Stop relying only on basic data | Continue consistent research | Explored multiple financial APIs
3 | S1 | 2026-02-01 | 2026-02-05 | Lokesh Avulapati | Start improving backend integration | Stop minor debugging delays | Continue API development work | Fixed API issues and improved integration
4 | S1 | 2026-02-01 | 2026-02-05 | Susekha P | Start enhancing UI design quality | Stop basic UI layouts | Continue frontend development | Improved dashboard design
5 | S1 | 2026-02-01 | 2026-02-05 | Zakkireddy Srihitha Reddy | Start detailed documentation | Stop minimal documentation | Continue testing support | Created structured documentation
6 | S1 | 2026-02-01 | 2026-02-05 | Yash Kumar | Start learning UI basics | Stop inconsistent work | Continue assisting team | Completed basic UI tasks