## Product Backlog
PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Fetch historical stock & ETF data | Must | API | SRIHITHA | Done
S1 | S1 | US-02 | Preprocess financial data | Must | US-01 | SRIHITHA | Done
S1 | S1 | US-03 | Visualize stock trends | Should | US-01 | SRIHITHA | Done
S2 | S2 | US-04 | Build ML model | Must | US-02 | SRIHITHA | In Progress
S2 | S2 | US-05 | Feature engineering | Must | US-02 | SRIHITHA | In Progress
S2 | S2 | US-06 | Evaluate performance | Should | US-04 | SRIHITHA | Pending
S3 | S3 | US-07 | Generate signals | Must | US-04 | SRIHITHA | Pending

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11
SPRINT 1 BACKLOG
US-01 | T-01 | Setup project | 2026-02-18 | 2026-02-22 | SRIHTIHA | Setup | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Fetch data | 2026-02-24 | 2026-03-02 | SRIHTIHA | Development | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Preprocessing | 2026-03-04 | 2026-03-09 | SRIHTIHA | Development | Done | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | API issue | Resolved API
Sprint 1 | Day 2 | Missing data | Cleaned dataset

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 01-04-2026 | 04-04-2026 | Self | Planning | Delays | Daily updates | Improved scheduling